## Project Planner
EduCare
| AI Tutor and Health Assistant for Autism Support |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
| ACTIVITY | PLAN START | PLAN DURATION (week) | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
| Working on idea | 1 | 1 | 1 | 1 | 100%
| Finalizing Idea | 1 | 1 | 1 | 1 | 100%
| Working on features and Competitors | 3 | 2 | 4 | 2 | 100%
| Finalize Project Proposal | 4 | 1 | 4 | 1 | 100%
| Documentation | 4 | 7 | 10 | 3 | 50%
| Assessment Feature | 4 | 1 | 5 | 1 | 100%
| Design UI/UX | 5 | 2 | 5 | 3 | 100%
Chatbot Development
| Design Chatbot Conversation Flow | 6 | 2 | 6 | 1 | 100%
| Implement Chatbot | 7 | 2 | 6 | 1 | 100%
AI Tutor Development
| Develop Personalized Learning Modules | 8 | 2 |  | 0 | 0%
| Implement Interactive Games | 9 | 3 |  | 0 | 0%
Progress Tracking
| Design Progress Tracking Feature | 10 | 1 |  | 0 | 0%
| Implement Data Logging Mechanism | 11 | 2 |  | 0 | 0%
| Develop Progress Reporting | 12 | 1 |  | 0 | 0%
Testing & QA
| Create Testing Plan | 13 | 2 |  | 0 | 0%
| Conduct Testing and Quality Assurance | 14 | 2 |  | 0 | 0%
Final Documentation
| Prepare User Manual | 15 | 2 |  | 0 | 0%
| Compile Project Report | 16 | 2 |  | 0 | 0%
Project Submission
| Submit Final Project | 17 | 2 |  | 0 | 0%
| Activity 19 |  |  |  | 0 | 0%
| Activity 20 |  |  |  |  | 0%
Each task is performed by all groups members
| Documentation completed 20 december | 12 weeks is starting from 28 sep